## Sheet1
Day | Date | From | Until | What did we do? | Participants | To do's | Deadline | For | Time needed | Reason
[6 empty] | Adjust agenda + send agenda + send email to client | 2022-10-11 | Alexander
[6 empty] | Adjust git |  | Aya | 30 minutes
Monday | 2022-10-10 | 2.3 | 3 | Discussed plans | Alaa
|  |  |  | Approved interview questions | Aya
|  |  |  | Decided to make the test report tomorrow after school at 16 | [5 empty] | Erfan and Alexander weren't at school for unknown reason
Thursday | 2022-10-13 | 10.3 | 11 | We split the test cases | Erfan | Test the first 4 test cases + write recommendation |  | Erfan |  | Alexander wasn’t at school for unknown reason
[5 empty] | Alaa | Test the second 4 test cases + + write recommendation |  | Alaa |  | We couldn’t test the program because the application didn’t work
[5 empty] | Aya | Test the last 4 test cases + + write recommendation |  | Aya
Friday | 2022-10-14 | 2 | 2.3 | Discussed new requirments | Alaa | Tutor meeting notes + Turor meeting agenda + working hours + send agenda to tutor | 2022-10-21 | Alaa | 1 hours
[5 empty] | Aya | Client meeting notes + Database design |  | Erfan | 6 hours
[5 empty] | Alex (until 11.45) | URS + project plan |  | Aya | 4 hours
[5 empty] | Erfan | Tickets |  | Alexander
Friday | 2022-10-21 | 10 | 11.3 | Tutor meeting | Alaa | Finilize the database design + make CRUD functionalities + make the code and the database design the same | 2022-10-24 | Erfan | 5 hours
|  |  |  | Split tasks | Aya | Meeting notes + agenda + update project plan + update URS + send agenda to tutor + send review email |  | Aya | 1 hour and 45 minutes
Erfan
[6 empty] | Make CRUD functionalities + Clean up the code + Complete the UI | 2022-10-26 | Erfan | 7 hours
[6 empty] | Update the general page for animals + Clean code + Implement health situation page | 2022-10-30 | Alaa | 6 hours
[6 empty] | Update workingHours + Implement feeding timetable + Clean code + Update navigation through pages | 2022-11-04 | Aya | 20 hours
[6 empty] | Fill process peer review form | 2022-11-03 | Aya | 30 minutes
[6 empty] | Fill process peer review form |  | Alaa
[6 empty] | Fill process peer review form |  | Erfan
[6 empty] | Fill process peer review form |  | Alexander
Friday | 2022-11-04 | 9.15 | 10.15 | Last check up | Alaa | send client interview email | 2022-11-07 | Aya | 5 minutes
|  |  |  | Totor meeting | Aya | Write meeting notes + write interview questions |  | Erfan
|  |  |  | Devided tasks | Erfan | make web application paper prototypes |  | Alaa
Wednesday | 2022-11-09 | 15.3 | 16 | Client meeting | Alaa | Project plan + agenda + email | 2022-11-16 | Aya | 1 hour
[5 empty] | Aya | URS |  | Alaa/Erfan
Erfan
Wednesday | 2022-11-16 | 11.3 | 12 | Tutor meeting | Alaa | agenda + email | 2022-11-18 | Aya | 10 minutes
|  |  |  | Split tasks | Aya | URS |  | Erfan/Alaa
[5 empty] | Erfan | Make website layout |  | Alaa
Friday | 2022-11-18 | 9.3 | 10.15 | Tutor meeting | Aya | Make employee schedule | 2022-11-25 | Erfan |  | Couldn't finish it on time because it takes more time than expected
|  |  |  | Split tasks | Erfan
[6 empty] | Fill up reflection document |  | Aya | 30 minutes
[6 empty] | Fill up reflection document |  | Alaa | 30 minutes
[6 empty] | Fill up reflection document |  | Erfan
[6 empty] | Write meeting notes for this meeting (x2) + write agenda + send email + complete project plan + Apply design/input validation feedback from client + Make attendance schedule + Process document | 11/24/2022 at 09.00 | Aya | 2 hours | The schedule is not done yet. That's why I cannot make the attendance page yet
[6 empty] | The login + employee page on website + upload paper prototytpes on git | 11/18/2022 | Alaa | 6h
[6 empty] | write client meeting notes + Apply code feedback from client + update URS |  | Erfan |  | Didn't have time to make thembecause the schedule is taking more time than expected
Thursday | 2022-11-24 |  |  | Made presentation | Alaa | make activity diagram + make process peer review document | 11/24/2022 before 19.00 | Aya
|  |  |  | Split script | Aya | make process peer review document |  | Alaa
[5 empty] | Erfan | make process peer review document |  | Erfan
[6 empty] | make use cases + write agenda + send email + write project plan | 2022-12-09 | Aya
[6 empty] | make use cases |  | Alaa
[6 empty] | make use cases |  | Erfan
Friday | 2022-12-09 | 9.3 | 10 | Tutor meeting | Aya | implement contact forms on website and desktop + write agenda + send email with agenda + write meeting notes + edit use cases | 2022-12-16 | Aya | 4 hours & 30 minutes
[5 empty] | Alaa | implement comments on website + implement tickets on website and desktop + edit use cases |  | Alaa |  | Didn't have time cz of synthesis assignment
[6 empty] | implement employee schedule |  | Erfan |  | Lost the code cz of git
[6 empty] | Write agenda and send an email with it | 2022-01-13 | Aya | 15 minutes
[6 empty] | Write the last version of the project plan |  | Alaa
[6 empty] | Write the last version of the URS |  | Erfan
[6 empty] | make the lastest version of the database design + write the notes until the last meeting |  | Erfan
[6 empty] | write the agenda's until the last meeting + send an email with the agenda until the last meeting + make the latest version of the UML diagram + update the working hours document until the last day |  | Aya | 5 hour
[6 empty] | make the last presentation + of the process report |  | Alaa
[6 empty] | show employees asked vacation + show employees preference day choices + send a real email with the tickets email address + add input validation + Make employee schedule automatic + split layers | 2023-01-19 | Erfan | 2 hours
[6 empty] | manage the tickets from the desktop application + edit the design + add search feature for health situation page + make feeding timetable automatic + Manage the reports |  | Aya | 9 hours 10 minutes
[6 empty] | add employee assigned to the feeding time on feeding timetable + send an email with the answer of the contact form + make employee schedule page + make an option for employees to be able to ask days off in vacations + make an option for employees to give a workday preference + make the report feature |  | Alaa